## Tennis - Product Backlog
Sl No | User Story | Story Points | Started On | Completed On | % Completion | Status | Comments
1 | Analysis & Understanding of Tennis Game |  | 2021-10-16 | 2021-10-17 | 100% | Completed | Watching tennis matches to understand the game
2 | Data Model Design |  | 2021-10-18 | 2021-10-19 | 100% | Completed | High level ER-Diagram
3 | High Level Class Diagram |  | 2021-10-18 | 2021-10-20 | 100% | Completed
4 | Point, Game & Set API |  | 2021-10-21 | 2021-10-24 | 100% | Completed | Writing test cases and implemenation of API's
5 | Match & Player API |  | 2021-10-21 | 2021-10-24 | 100% | Completed | Writing test cases and implemenation of API's. - Currently API is supports only starting of new match
6 | Business Rule Service Layer |  | 2021-10-24 | 2021-11-27 | 100% | Completed | Business logic layer to embed business rules
7 | Persistence Service Layer |  | 2021-10-30 | 2021-11-27 | 100% | Completed | Persistence layer to embed database operations to support multiple database
8 | Presentation Layer - WPF |  | 2021-11-14 | 2021-11-27 | 100% | Completed | View layer using WPF